## Breakdown
THE LAST SUMMER OF RATNAGIRI
10th April to 10th May 2026
DATE | DAY | LOCATION | FILM LOCATION | SHIFT TIMING | C1 | L1 | C2 | L2 | SL | JJ | DR | JR | PV | CR | HC | VFX | SFX | TS | CAST | SUPPORTING CAST | PICTURE VEHICLE | EXTRAS | NOTES
10th April | Shoot Day 1 | RATNAGIRI | VELNESHWAR BEACH | 6 AM to 6 PM | 1 | 1 | 1 | 1 | 1 |  | 1 | 25 | 1 |  | 1 |  |  | 1 | Aarav, Meera, Priya | Fisherman1, Fisherman2 | Aarav's Motorcycle, Fishing Boat | MOB - 25 (villagers) | Golden hour critical for closing shot.
11th April | Shoot Day 2 | RATNAGIRI | VELNESHWAR BEACH | 6 AM to 6 PM | 1 | 1 | 1 | 1 | SL: 1; DR: 1; JR: 40; PV: 1; HC: 1 | Aarav, Meera | Fisherman1 | Fishing Boat | MOB - 40 (tourists) | Weather window tight — rain backup: scene 14.
12th April | Shoot Day 3 | RATNAGIRI | BHAGAWATI MANDIR | 4 AM to 4 PM | 1 | 1 | 1 | 1 | JJ: 1; JR: 60; HC: 1; TS: 1 | Aarav, Meera, Priya, Dada | Priest, Singers x4 | Vintage Ambassador Car | MOB - 60 (devotees) | Temple permission — no shoes inside.
13th April | Shoot Day 4 | RATNAGIRI | DADA'S HOUSE | 9 AM to 9 PM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Dada, Aaji | Neighbor |  |  | Interior, no exterior noise — blankets on windows. | bar: SL; HC
14th April | Shoot Day 5 | RATNAGIRI | DADA'S HOUSE | 9 AM to 9 PM | 1 | 1 | [12 empty] | Aarav, Aaji |  |  |  | VFX plate shot of window — sun flare ref. | bar: HC to VFX
15th April | Break Day
16th April | Shoot Day 6 | RATNAGIRI | FORT / OLD RUINS | 6 AM to 6 PM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Meera, Antagonist | Guard, Tourists x2 | Aarav's Motorcycle | MOB - 15 (walkers) | Drone permits cleared; shot list A priority. | bar: SL to DR; CR to HC; TS
17th April | Shoot Day 7 | RATNAGIRI | FORT / OLD RUINS | 6 AM to 6 PM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Antagonist | Guard | Aarav's Motorcycle, Antagonist's Jeep |  | Action sequence — SFX squibs, rehearsal at 5 AM. | bar: JJ to DR; CR to HC; SFX to TS
18th April | Shoot Day 8 | GANPATIPULE | HIGHWAY / COASTAL ROAD | 6 AM to 6 PM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Meera |  | Aarav's Motorcycle, Meera's Scooter |  | Traffic control permit — highway 17. | bar: DR; PV; HC; TS
19th April | Shoot Day 9 | GANPATIPULE | COASTAL CAFE | 12 PM to 12 AM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Meera, Priya | Cafe Staff x2, Musicians x2 |  | MOB - 20 (cafe patrons) | Live music rehearsed previous day. | bar: SL; HC
20th April | Break Day
21st April | Shoot Day 10 | KOLHAPUR | UNIVERSITY COURTYARD | 9 AM to 9 PM | 1 | 1 | 1 | 1 | JJ: 1; JR: 80; HC: 1 | Aarav, Priya | Professor, Students x6 |  | MOB - 80 (students) | Convocation recreation scene.
22nd April | Shoot Day 11 | KOLHAPUR | UNIVERSITY CORRIDORS | 9 AM to 9 PM | 1 | 1 | [12 empty] | Aarav, Priya | Students x3 | bar: SL; HC
23rd April | Shoot Day 12 | KOLHAPUR | MAHALAKSHMI TEMPLE | 4 AM to 4 PM | 1 | 1 | 1 | 1 | JJ: 1; JR: 120; HC: 1; TS: 1 | Aarav, Meera, Dada | Priest, Family x5 | Vintage Ambassador Car | MOB - 120 (devotees) | Morning aarti at 5 AM — respect devotees.
24th April | Dance Rehearsal
25th April | Shoot Day 13 | KOLHAPUR | WEDDING HALL | 6 PM to 6 AM | 1 | 1 | 1 | 1 | 1 | 1 |  | 180 |  | 1 | 1 |  |  | 1 | Aarav, Meera, Dada, Aaji, Priya, Antagonist | Family x12, Band x6 | Vintage Ambassador Car, Decorated Horse Cart | MOB - 180 (wedding guests) | Song sequence — playback coordinated with band.
26th April | Shoot Day 14 | KOLHAPUR | WEDDING HALL | 6 PM to 6 AM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Meera, Priya | Family x6 |  | MOB - 80 (wedding guests) | Emotional sequence — closed set. | bar: SL; HC to VFX
27th April | Break Day
28th April | Shoot Day 15 | MUMBAI | CST STATION | 4 AM to 4 PM | 1 | 1 | 1 | 1 | SL: 1; JJ: 1; JR: 100; HC: 1; TS: 1 | Aarav | Porter, Travellers x4 | Local Train Replica | MOB - 100 (commuters) | Station permit 4-8 AM only — strict window.
29th April | Shoot Day 16 | MUMBAI | BANDRA STREETS | 12 PM to 12 AM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Meera | Street Vendor, Shopkeeper | Aarav's Motorcycle, Taxi |  | Night-time street shoot — traffic police cleared. | bar: SL; DR; HC
30th April | Shoot Day 17 | MUMBAI | CAFE MONDEGAR | 6 PM to 6 AM | 1 | 1 | [12 empty] | Aarav, Meera | Waiter |  | MOB - 30 (cafe patrons) | Intimate dialogue scene. | bar: HC
1st May | Shoot Day 18 | MUMBAI | MARINE DRIVE | 6 PM to 6 AM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Meera |  | Aarav's Motorcycle | MOB - 40 | Iconic shot — queen's necklace pan. | bar: JJ to DR; HC; TS
2nd May | Break Day
3rd May | Shoot Day 19 | FILM CITY MUMBAI | SET A — APARTMENT | 9 AM to 9 PM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Priya |  |  |  | Controlled interior — pickup shots. | bar: SL; HC
4th May | Shoot Day 20 | FILM CITY MUMBAI | SET B — OFFICE | 9 AM to 9 PM | 1 | 1 | [12 empty] | Aarav | Colleagues x3 |  |  | VFX backdrop plate. | bar: HC to VFX
5th May | Shoot Day 21 | FILM CITY MUMBAI | SET A — APARTMENT | 9 AM to 9 PM | 1 | 1 | 1 | 1 | [10 empty] | Aarav, Meera, Priya, Antagonist |  |  |  | Climax confrontation scene. | bar: SL; HC to VFX
6th May | Shoot Day 22 | FILM CITY MUMBAI | SET C — HOSPITAL | 6 AM to 6 PM | 1 | 1 | [12 empty] | Aarav, Dada, Aaji | Doctor, Nurses x2 |  |  | Final scene. | bar: HC

## Cast List
CAST / CHARACTERS
# | CHARACTER | NAME
1 | Aarav | SIDDHARTH CHANDEKAR
2 | Meera | AMRUTA KHANVILKAR
3 | Priya | SHRUTI MARATHE
4 | Dada | MOHAN AGASHE
5 | Aaji | ROHINI HATTANGADI
6 | Antagonist | ABHIJEET KHANDKEKAR